## Dashboard
Software Department – MIS Dashboard
Reporting Period: August 2026 ¦ Report Date: 05-Aug-2026
Project Portfolio |  | Resource Utilization |  | Quality / Defects
Total Projects | 3 | Team Headcount | 18 | Total Defects Logged | 1
On Track | 2 | Avg Allocation % | 100% | Open | 0
At Risk | 0 | Avg Utilization % | 54.27% | In Progress | 0
Delayed | 1 | Total Billable Hrs | 148 | Closed | 1
Avg % Complete | 72.5% | Total Non-Billable Hrs | 275 | Critical & Open | 0
Hours Variance % | -12.5% | Over-allocated Staff | 0 | SLA Breaches | 1
|  | Hours Variance % | -67.62% | SLA Compliance % | 0%
Chart Source Data (auto-computed – do not edit)
Project RAG Status |  | Defect Severity (Open Items) |  | SLA Status Breakdown
On Track | 0 | Critical | 0 | Met | 0
At Risk | 0 | High | 0 | Within SLA | 0
Delayed | 0 | Medium | 0 | Breached | 1
|  | Low | 0

## Project Status
Software Department – Project Status
Reporting Period: August 2026 ¦ Report Date: 05-Aug-2026
S.No | Project Name | Project Manager | Planned Activities | Start Date | Planned End Date | % Complete | Planned Hours | Utilized Hours | Hours Variance | Variance % | Status (RAG) | Milestone Achieved | Remarks
1 | MAKO - Phase 3 | Renuka | IBIS World integration Plaid integration | 2026-08-01 | 2026-08-31 | 75% | 160 | 140 | -20 | -12.5% | On Track | IBIS World Integration Plaid integration - In Progress User journey - In Progress | On schedule
2 | Revalix 1.0 | Renuka | Report Features FCV - Commercial Summary Report Cost Approach Revalix - Eval Report Revalix Data - Batch data integration, Web search - data fields | 2026-08-01 | 2026-08-31 | 70% |  |  |  |  | Delayed | Report Features FCV - Commercial Summary Report Cost Approach Revalix - Eval Report Revalix Data - Batch data integration, Web search - data fields | On schedule
3 | Revalix 2.0 | Renuka | New UI, Data Integration,AI integration | 2026-08-24 | 2026-08-31 | [5 empty] | On Track | Property data - In Progress | On schedule
On schedule

## Resource Utilization
Software Department – Resource Utilization
Reporting Period: August 2026 ¦ One row per employee-project assignment — the same employee can appear on multiple rows
160
S.No | Employee Name | Role | Project Allocated | Allocation % | Planned Hours | Billable Hours | Non-Billable Hours | Actual Hours | Hours Variance | Variance % | Leave/ Permission | Function | 16
1 | Renuka | Project Manager | Revalix 1.0 | 10% | 16 |  | 16 | 16 | 0 | 0%
2 | Renuka | Project Manager | Revalix 2.0 | 30% | 48 |  | 48 | 48 | 0 | 0%
3 | Renuka | Project Manager | MAKO | 40% | 64 |  | 64 | 64 | 0
4 | Renuka | Project Manager | General | 10% | 16 |  | 16 | 16 | 0 | 0%
4 | Renuka | Project Manager | ValBox | 10% | 16 |  | 16
5 | Dinesh N | Software Developer | Revalix 1.0 | 70% | 112 |  | 29 | 29 | 83 | 74.11% | 8 | 3
| Dinesh N | Software Developer | Revalix 2.0 | 30% | 48
6 | Vinodkumar G | Software Developer | Revalix 1.0 | 70% | 112 |  | 7 | 7 | 105 | 93.75% | 8 | 5
7 | Vinodkumar G | Software Developer | Revalix 2.0 | 20% | 32 |  | 18 | 18 | 14
8 | Vinodkumar G | Software Developer | Training | 10% | 16 |  | 2 | 2 | 14
9 | Aravinthan A | Jr.Software Developer | Revalix 1.0 | 100% | 160 |  | 30 | 30 | 130 | 81.25% |  | 8
10 | Srisabarish V | Jr.Software Developer | Revalix 1.0 | 100% | 160 |  | 29 | 29 | 131 | 81.88% | 8 | 3
11 | Sripathi | Jr.Software Developer | Revalix Data | 95% | 152 |  | 18 | 18 | 134 | 88.16% |  | 5
12 | Sripathi | Jr.Software Developer | Revalix 2.0 | 5% | 8 |  | 16 | 16 | -8 | -100%
13 | Roshan | Jr.Software Developer | Revalix 2.0 | 5% | 8 |  | 16 | 16 | -8 | -100% | 8 | 7
14 | Roshan | Jr.Software Developer | Finance | 5% | 8 |  | 9 | 9 | -1 | -12.5%
| Roshan | Jr.Software Developer | Revalix Data | 90% | 144
15 | Joetheeswaran | Jr.Software Developer | Revalix Data | 90% | 144 |  | 28 | 28 | 116 | 80.56% |  | 12
16 | Joetheeswaran | Jr.Software Developer | Revalix 2.0 | 10% | 16 |  |  | 0 | 16 | 100%
17 | Raghul | Software Developer | MAKO Phase 3 | 100% | 160 | 35 |  | 35 | 125 | 78.12% | 2 | 3
18 | Praveen Kumar | Software Developer | MAKO Phase 3 | 100% | 160 | 37 |  | 37 | 123 | 76.88% |  | 3
19 | Saradha | Intern | Revalix 1.0 | 10% | 16 |  | 5 | 5 | 11 | 68.75% | 10 | 5
20 | Saradha | Intern | Training | 90% | 144 |  | 20 | 20 | 124 | 86.11%
21 | Kirubesh | Software Developer | Modum | 100% | 160 | 160 |  | 160 | 0 | 0%
22 | Deepak | CRM Developer | FCV | 100% | 160 | 160 |  | 160 | 0 | 0%
23 | Athish | Intern | Training | 100% | 80 |  | 80 | 80 | 0 | 0%
24 | Joeyln | Intern | Training | 100% | 80 |  | 80 | 80 | 0 | 0%
25 | Chandru | Intern | Training | 100% | 80 |  | 80 | 80 | 0 | 0%
26 | Sanjay | Intern | Training | 100% | 80 |  | 80 | 80 | 0 | 0%
27 | Ananya | Intern | Training | 100% | 80 |  | 80 | 80 | 0 | 0%
Employee Allocation Summary (auto-computed – add a row here if you add a new employee)
S.No | Employee Name | Role | Total Allocation % | Planned Hours | Actual Hours | Hours Variance | Variance % | Standard Hours | Utilization % | Allocation Status
1 | Renuka | Project Manager | 100% | 160 | 144 | -16 | -10% | 160 | 90% | Fully Allocated
2 | Vinodkumar G | Software Developer | 100% | 160 | 27 | -133 | -83.12% | 160 | 16.88% | Fully Allocated
3 | Dinesh N | Software Developer | 100% | 160 | 29 | -131 | -81.88% | 160 | 18.12% | Fully Allocated
4 | Srisabarish V | Jr.Software Developer | 100% | 160 | 29 | -131 | -81.88% | 160 | 18.12% | Fully Allocated
5 | Aravinthan A | Jr.Software Developer | 100% | 160 | 30 | -130 | -81.25% | 160 | 18.75% | Fully Allocated
6 | Sripathi | Jr.Software Developer | 100% | 160 | 34 | -126 | -78.75% | 160 | 21.25% | Fully Allocated
7 | Roshan | Jr.Software Developer | 100% | 160 | 25 | -135 | -84.38% | 160 | 15.62% | Fully Allocated
8 | Joetheeswaran | Jr.Software Developer | 100% | 160 | 28 | -132 | -82.5% | 160 | 17.5% | Fully Allocated
9 | Raghul | Software Developer | 100% | 160 | 35 | -125 | -78.12% | 160 | 21.88% | Fully Allocated
10 | Praveen Kumar | Software Developer | 100% | 160 | 37 | -123 | -76.88% | 160 | 23.12% | Fully Allocated
11 | Saradha | Intern | 100% | 160 | 25 | -135 | -84.38% | 160 | 15.62% | Fully Allocated
13 | Kirubesh | Software Developer | 100% | 160 | 160 | 0 | 0% | 160 | 100% | Fully Allocated
14 | Deepak | CRM Developer | 100% | 160 | 160 | 0 | 0% | 160 | 100% | Fully Allocated
15 | Athish | Intern | 100% | 80 | 80 | 0 | 0% | 80 | 100% | Fully Allocated
16 | Joeyln | Intern | 100% | 80 | 80 | 0 | 0% | 80 | 100% | Fully Allocated
17 | Chandru | Intern | 100% | 80 | 80 | 0 | 0% | 80 | 100% | Fully Allocated
18 | Sanjay | Intern | 100% | 80 | 80 | 0 | 0% | 80 | 100% | Fully Allocated
19 | Ananya | Intern | 100% | 80 | 80 | 0 | 0% | 80 | 100% | Fully Allocated

## Defect Tracking
Software Department – Defect / Quality Tracking
Reporting Period: August 2026 ¦ Report Date: 05-Aug-2026
S.No | Defect ID | Project | Severity | Status | Reported Date | Resolved Date | Ageing (Days) | SLA Target (Days) | SLA Variance (Days) | SLA Status | Assigned To
1 | DEF-1001 | Revalix | Critical | Closed | 2026-08-10 | 2026-08-13 | 1 | 0 | -1 | Breached | Dinesh
SLA Policy (editable – target resolution days by severity)
Severity | Target (Days)
Critical | 0
High | 1
Medium | 0
Low | 0